I N S T A Q U I R K

WorkStay

Delivery Plan — Milestones, Timeline, and Open Points

Prepared for Robert Moses  •  28 July 2026  •  Responding to the Lean MVP Website Specification (7/27/2026)

Robert — you asked for two things: estimated time for each milestone, and my comments on anything the spec leaves open. Both are here, and I have kept this short deliberately.

I have also combined your five milestones into three. Your milestones 3 and 4 cannot really be separated — proximity filtering is a search feature and needs the listing data in place before it works at all. Splitting them would give you a checkpoint you could only half test. Three gives you three points where the product genuinely does something new. Every acceptance test you wrote is preserved.

THE SHORT VERSION Eight weeks from kickoff to a live site, in three milestones. Around 12 to 15 hours of your time in total — roughly 90 minutes a week. Twelve points the spec leaves open, each with my recommended answer already filled in, so agreeing is enough. One of them (how renters text landlords) has a real cost consequence and is worth two minutes of your attention.

## The plan at a glance

| Milestone | What gets built | Time | What you can do at the end |
| --- | --- | --- | --- |
| 1. Foundation | Discovery, full site design, landlord sign-up and login, Stripe membership billing | 13 days approx. 2.5 wks | Sign up as a test landlord, pay with a test card, cancel, and watch your status update |
| 2. Core build | Listings, photos, search, filters, medical facility distances, inquiries | 18 days approx. 3.5 wks | Post a real property, search and filter for it, sort by distance from a hospital, send an inquiry |
| 3. Launch | Admin controls, testing, going live, training, handover | 11 days approx. 2 wks | Run the business yourself: approve listings, manage members and facilities, edit page text |

Total: 42 working days, approximately 8 calendar weeks from kickoff to launch.

# 1. Time Estimates by Milestone

Days below are project working days, with parallel workstreams already accounted for. They assume feedback within two business days at each checkpoint.

## Milestone 1 — Foundation

13 working days  ·  approx. 2.5 weeks  ·  30% of contract value

| Work item | Days |
| --- | --- |
| Kickoff, confirming scope, finalizing exactly what information a listing holds | 2.0 |
| Site structure, page list, documented journeys for renter, landlord and admin | 1.5 |
| Design of every screen: homepage, search results, listing page, landlord dashboard, sign-up and login, content pages | 4.0 |
| Hosting and staging site, security setup, backups, email delivery configuration | 1.5 |
| Stripe setup: products, pricing, checkout, and correct handling of failed, canceled and expired payments | 2.0 |
| Sign-up, login, password reset, profile, landlord dashboard showing live membership status | 2.0 |
| Milestone 1 total | 13.0 |

Acceptance: you approve the designs and page flows before the main build starts, and a test subscription can be started, canceled, failed, and shown correctly in the dashboard.

## Milestone 2 — Core Build

18 working days  ·  approx. 3.5 weeks  ·  45% of contract value

| Work item | Days |
| --- | --- |
| Listing structure and all fields; photo upload, reordering, automatic resizing and compression | 3.0 |
| Landlord listing management: create, edit, preview, publish, pause, delete, with drafts and pending-approval states | 3.0 |
| Public listing page: gallery, key facts, description, map area, nearby facilities, inquiry form | 3.0 |
| Search results and every filter — price, bedrooms, bathrooms, type, pet policy, availability — plus all four sort options | 3.5 |
| Address-to-coordinate conversion, the facility list you manage yourself, distance sorting and filtering | 3.5 |
| Inquiry system: form, spam protection, email to landlord with optional copy to you, text-the-landlord option | 1.5 |
| Automatic hiding of listings when a membership lapses, and restoring them on renewal | 0.5 |
| Milestone 2 total | 18.0 |

Acceptance: end-to-end landlord and renter flows work on the test site, and distances are accurate for an agreed set of Pittsburgh test addresses.

## Milestone 3 — Launch

11 working days  ·  approx. 2 weeks  ·  25% of contract value

| Work item | Days |
| --- | --- |
| Admin area: approval queue, moderation, member overview, facility management, dashboard totals | 3.0 |
| Search engine setup, clean web addresses, sitemap, analytics | 1.5 |
| Testing across browsers and phones, accessibility review, fixing everything found | 3.0 |
| Switching Stripe to live payments, launching on your domain, backups and uptime monitoring | 1.5 |
| Written documentation, recorded training session, transfer of every account and credential to you | 2.0 |
| Milestone 3 total | 11.0 |

Acceptance: your MVP checklist is fully satisfied, no critical defects remain, and you control every account, the source code, the database and the documentation.

WHAT THE EIGHT WEEKS ASSUMES Feedback within two business days at each checkpoint, and two items arriving on time: your Stripe account (created in week 1, verification can take days) and your Terms and Privacy text from your attorney. Both depend on third parties neither of us can speed up, which is exactly why I would start both in week 1 rather than when they are needed.

# 2. What the Spec Leaves Open

Your spec is more thorough than most I receive. These are the points it does not settle, or where it could be read two ways. Each has my recommended answer — what I would choose if this were my own business, and what I will build unless you say otherwise.

THE EASY PATH If nothing here gives you pause, reply "go with your recommendations" and we are done. You do not need to research anything or form a view on the technical items. Only items 1 to 4 need settling before we start; the rest we can cover on the kickoff call.

## Needed before we start

| # | Open point | My recommendation | Why |
| --- | --- | --- | --- |
| 1 | Final site name and domain — is "WorkStay" confirmed? | Confirm now and secure the domain in your name | Touches hosting, Stripe, email and every page of the design. Changing it later means redoing several things at once. |
| 2 | Membership price, and monthly or annual? | Offer both, with two months free on annual | Monthly lowers the barrier to joining; annual improves cash flow and reduces churn. Equally easy to set up now. |
| 3 | How many listings does one membership include? | One tier, up to 3 listings | Covers the typical small landlord. More tiers are simple to add once you see who actually signs up. |
| 4 | Should the site send texts to landlords, or open the renter’s own phone? | Open the renter’s own phone | The only item here with a real cost consequence — explained below. |

## Needed in the first two weeks

| # | Open point | My recommendation | Why |
| --- | --- | --- | --- |
| 5 | Which medical facilities launch on the site? | Major hospital campuses first; clinics and rehab later | Distances only help if renters recognize the names. Adding more later takes minutes and needs no developer. |
| 6 | How many nearby facilities should a listing show? | The three nearest, within 15 miles | One feels thin, ten is clutter. Three answers the renter’s question at a glance. |
| 7 | Straight-line distance or driving time? | Straight-line for search, driving time on the listing page | Straight-line is instant and free, which is what search needs. Driving time is what matters once a renter is interested in one property. |
| 8 | Should the exact street address be public? | Show neighborhood and a general map area only | A furnished rental that is often empty, with its address published, is an easy target. Full address goes to the renter after contact. |
| 9 | How long after a failed payment before listings come down? | Seven days | Gives Stripe time to retry an expired card and the landlord time to notice. |
| 10 | What happens to listings when a membership lapses? | Hidden, restored instantly on renewal | If someone loses an hour of work because their card expired, they do not come back. |
| 11 | Who writes the site copy? | I draft, you edit — already included | Reacting to a draft is far easier than writing from nothing. This is the most common thing that stalls a finished site. |
| 12 | Should edits to a live listing need re-approval? | Price and availability go live instantly; address, title and photos flag for your review | Approving every edit buries you in admin. Approving none means a listing could be quietly rewritten. |

## The one item worth two minutes: texting the landlord

Your spec asks for an option for renters to text the landlord. That can mean two quite different things, and the gap between them is large enough that I did not want to assume.

| What it could mean | Effort | Consequence |
| --- | --- | --- |
| A. Tapping a button opens the renter’s own messaging app with the landlord’s number filled in. The message comes from the renter’s phone. | A few hours | No ongoing cost, no approval process. The landlord’s number appears on the listing. |
| B. The website itself sends the text, keeping the landlord’s number private. | Substantial | US carriers require formal registration for business texting. Needs a tax ID, carries fees and per-message costs, and approval commonly takes one to three weeks. |

IN PLAIN TERMS Option A is what I recommend for launch. Option B puts your launch date in a phone carrier’s approval queue that neither of us can influence. It is a perfectly reasonable feature to add in a few months, once you have real landlords and know whether keeping their numbers private is something they actually ask for. If we go with A, I would reveal the number on a click rather than leave it sitting in the page for spam bots to harvest.

## Three things I would add that the spec does not mention

- Proper email delivery. Emails from a brand new domain land in spam a meaningful share of the time. If a landlord pays and never receives their inquiries, they cancel — and it reads as the product failing when it is really an email setup issue. I include a dedicated sending service with proper authentication in milestone 1. Free tiers cover launch volumes.

- A Fair Housing notice and acknowledgment. A product observation rather than legal advice, and your attorney should confirm it — but US rental platforms carry exposure from descriptions written by landlords. A footer notice plus a required checkbox at listing submission costs a few hours now and is much harder to retrofit later. Worth raising alongside your Terms of Use.

- Presets built around the 13-week contract. Your renters are largely travel nurses and allied health contractors, and their contracts are almost always thirteen weeks. The minimum-stay filter should offer that as an option rather than making someone work out whether "3 months" is close enough. Trivial to build, and it makes the site feel made for the person using it.

# 3. How We Would Work Together

You mentioned you are not especially technical and want to know where you would need to support the work. Here is the honest picture.

## Your time commitment: 12 to 15 hours across eight weeks

| What you do | When |
| --- | --- |
| Kickoff call — I walk you through the plan and confirm decisions | Week 1 |
| Confirm the open points in Section 2 (most just need a yes) | Week 1 |
| Review and approve the site design | Week 2 |
| Try out sign-up and billing on the test site | Week 3 |
| Send me your medical facility list and a few test addresses | Week 3 |
| Review the site copy I draft for you | Week 4 to 5 |
| Try out listings, search and inquiries on the test site | Week 6 |
| Final walkthrough before launch | Week 7 |
| Training session — recorded, so you can rewatch it | Week 8 |

Nothing on that list requires technical skill. The reviews are you using the site the way a landlord or renter would, and telling me what feels wrong. That is the most useful thing you can give me, and you are better placed to do it than I am — you know this market and I do not.

## The rhythm

- You see the site being built. From week two you have a private link to a working copy that only we can see. Open it any time. Nothing is hidden until the end.

- A written update every Friday. What was done, what is next, anything I need from you, anything that could affect the date. A few minutes to read.

- Reviews come with instructions. I send a link and a short checklist of things to try, written as plain steps. You reply however is easiest — a list, screenshots, or a call. "This button confuses me" is genuinely useful feedback.

- Time zones work in your favor. My team is ten hours ahead of Pittsburgh, so my day ends as yours begins and you tend to wake up to progress. For calls, I am available 8am to 11am your time on weekdays, and will make other times work.

- New ideas get written down, not absorbed silently. You will have ideas around week four — everyone does. Small ones I will simply build. Larger ones I will tell you plainly what they would cost in time, so you decide with real information. Nothing gets lost and nothing quietly derails the launch.

## Where projects like this usually get stuck

So you know what to watch for. None of these are reasons not to proceed.

| Risk | Why it happens | How we avoid it |
| --- | --- | --- |
| Legal text arriving late | Attorneys work to their own schedule. This is the most common reason a finished site sits unlaunched. | Send the request in week 1. I will give your attorney a written summary of what the site does and what data it collects. |
| Stripe verification | Stripe asks for business documents and a tax ID. Usually a day or two, occasionally weeks. Neither of us controls it. | Create the account in week 1. We build and test everything in Stripe test mode, which needs no verification. |
| Not knowing what the site should say | Writing marketing copy from a blank page is genuinely hard and stalls projects that were otherwise on schedule. | I draft all of it, you edit. Already included in the plan. |
| Launching to an empty marketplace | On day one the site works perfectly and has no listings. Renters find nothing; landlords see no audience. | Decide before launch how the first 10 to 20 listings arrive. A founding-member discount costs nothing to set up in Stripe and gives you a reason to reach out. |

# 4. Ownership, Running Costs, and Support

## Ownership

Every account is created in your name from the start rather than transferred at the end — domain, hosting, Stripe, mapping, email, analytics and the code repository. There is no handover moment where something could be forgotten, because nothing is ever in my name.

At completion you receive the full source code, database access, design files, all credentials, and written documentation. Nothing depends on an Instaquirk service or license. If you never speak to me again after launch, everything keeps working and any competent developer can pick it up.

## What you pay others each month

These go to third parties directly, not through me. The build is deliberately designed to keep every one on a free or entry tier at launch volumes.

| Service | What it does | Expected at launch |
| --- | --- | --- |
| Domain | Your web address | Roughly $15 per year |
| Hosting | Runs the website | Roughly $20 to $35 per month |
| Stripe | Collects membership payments | No monthly fee; standard rate per transaction |
| Maps | Address coordinates and distances | Expected within the free monthly allowance |
| Email delivery | Sends inquiries and account emails | Free tier covers launch volumes |
| Software licenses | Supporting components | Under $100 per year |

I will confirm exact figures and current limits in writing before anything is bought, and nothing recurring is signed up for without your approval. Figures above are indicative and should be verified at the point of purchase.



After launch

30 days of defect correction from the launch date, covering anything in the agreed scope that does not behave as specified. I respond within one business day, and start immediately on anything that stops a landlord subscribing or a renter inquiring.

Not covered: new features or changes to agreed behavior, outages at third-party services, content edits and day-to-day administration, or issues caused by changes others make after handover.

Ongoing maintenance beyond that is available on a monthly retainer, quoted separately once you know what level of support you actually want. I would not ask you to commit to that before you have seen how much you need it.

Sakib

Instaquirk